## SAP
Looply Implementation Plan (with SAP plugin)
Week
Mobilisation |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
| Mobilise team, arrange & test access to relevant systems | Arch / Customer | bar: Week 1
| Set up sharepoint folder/site as required | Arch / Customer | bar: Week 1
| Set up tool/system for capturing Design Issues | Arch / Customer | bar: Week 1
| Set up tool/system for capturing Test Issues and Change Requests | Arch / Customer | bar: Week 1
| Set up recurring meetings | Arch / Customer | bar: Week 1
| Determine success criteria in the case of a POC/Trial | Arch / Customer | bar: Week 1
| Agree pricing and issue purchase order | Arch / Customer | bar: Week 1
Discovery
Infrastructure | bar: Week 2
| Determine Looply deployment model to be used (see Deployment Model sheet) | Arch / Customer | bar: Week 2
| Liason with Azure and Security teams: | Arch / Customer | bar: Week 2
| Determine Azure / Teams security needs | Arch / Customer | bar: Week 2
| Determine relevant system landscape | Arch / Customer | bar: Week 2
| Determine required integrations & authenticate model for each integration | Arch / Customer | bar: Week 2
| Determine how many Teams apps are required | Arch / Customer | bar: Week 2
| Determine Teams app requirements (privacy policy / terms of use policy / domain whitelist) | Arch / Customer | https://academy.looply.ai/app-management/building-apps
Process
| Review project deliverables / capture requirements | Arch / Customer | bar: Week 2
| Define process and data flows | Arch / Customer | bar: Week 2
| Determine integration points | Arch / Customer | bar: Week 2
| Define requirements for Looply workflows | Arch / Customer | bar: Week 2
| Define requirements for Looply cards | Arch / Customer | bar: Week 2
| Define requirements for Looply apps | Arch / Customer | bar: Week 2
| Define administration process | Arch / Customer | bar: Week 2
Installation
| Set up private cloud deployment if required [Not for POC] | Arch
| Sign-up to Looply | Customer | https://dashboard.looply.ai/sign-up
| Invite team members to Looply workspace | Customer | https://academy.looply.ai/team-management/managing-organisations
| Provision Looply plan to customer workspace | Arch
| Configure Teams Integration | Arch / Customer | https://academy.looply.ai/integrations/microsoft-integration
| Configure Teams App & deploy to developer users. | Arch / Customer | https://academy.looply.ai/app-management/building-apps
| Generate API key | Arch / Customer | https://academy.looply.ai/api-reference/developer-api-overview
| Install Looply plug-in in development system | Customer | https://academy.looply.ai/integrations/sap-integration/installing-the-abap-looply-add-on
| Activate SICF nodes and Gateway Service | Customer | https://academy.looply.ai/integrations/sap-integration/installing-the-abap-looply-add-on
| OAuth2 client set up | Customer
| OAuth2 identity provider set up if required | Customer
| Create proxy endpoints if required | Customer
| Create RFC destination | Customer | https://academy.looply.ai/integrations/sap-integration/installing-the-abap-looply-add-on
| Configure Looply API key | Customer | https://academy.looply.ai/integrations/sap-integration/installing-the-abap-looply-add-on
| Configure SAP integrations in Looply for each SAP system / client | Customer
| Maintain number range | Customer | https://academy.looply.ai/integrations/sap-integration/installing-the-abap-looply-add-on
| Assign s_service to a new or existing role | Customer
| Assign Looply role to development users | Customer
Design
| Document system architecture and any proxies required for communication | Arch / Customer
| Document integrations and authentication approaches | Arch / Customer
| Design API payload for Looply trigger(s) | Arch / Customer
| Design Looply workflow(s) | Arch / Customer
| Design Looply card(s) | Arch / Customer
Build
| Build Looply workflow(s) | Arch / Customer | bar: Week 4 to Week 5
| Build Looply card(s) | Arch / Customer | bar: Week 4 to Week 5
| Configure event linkages or workflows for Looply trigger points | Arch / Customer | bar: Week 4 to Week 5
| Build outbounf functions in SAP and configure Looply processing table | Arch / Customer | bar: Week 4 to Week 5
| Build inbound functions in SAP and configure Looply processing table | Arch / Customer | bar: Week 4 to Week 5
| Plan and execute integration testing | Arch / Customer | bar: Week 4 to Week 5
Test
| Plan user acceptance testing | Customer | bar: Week 4 to Week 5
| Migrate Looply and project transport requests to SAP test system | Customer | bar: Week 6 to Week 7
| Set up number range | Customer | bar: Week 6 to Week 7
| Set up test data | Customer | bar: Week 6 to Week 7
| Assign Looply role to test users | Customer | bar: Week 6 to Week 7
| Deploy Teams app to test users | Customer | bar: Week 6 to Week 7
| Execute & Support user acceptance testing | Arch / Customer | bar: Week 6 to Week 7
Cutover
| Create and execute change management plan | Customer | bar: Week 4 to Week 8
| Deploy Teams app to production users | Customer | bar: Week 8
| Deploy locked versions of Looply workflows and cards | Arch / Customer | bar: Week 8
| Migrate SAP changes to production system | Customer | bar: Week 8
| Set up / check number range | Customer | bar: Week 8
| Assign Looply role to production users | Customer | bar: Week 8
| Knowledge transfer preparation and delivery | Arch / Customer | bar: Week 8 to Week 9
| Go-live support and hypercare | Arch / Customer | bar: Week 8 to Week 9